## Sheet1
Model Name | Time to Model | Time to UV | Time to Texture | Time to Implement | Adjustments | Total Time | Hours | Mins
Corridor Walls | 4 hours | 30 mins | 1 hour | 10 mins | 10 mins | 5 hours 50 mins | 5 | 50
Corridor Cielings | 4 hours | 30 mins | 1 hour | 10 mins | 10 mins | 5 hours 50 mins | 5 | 50
Corridor Curved Wall | 4 hours | 30 Mins | 1 hour | 10 mins | 10 mins | 5 hours 50 mins | 5 | 50
Trash Can | 1 hour | 10 mins | 20 mins | 5 mins | 5 mins | 1 hour 40 mins | 1 | 40
Bench | 1 hour | 10 mins | 20 mins | 5 mins | 5 mins | 1 hour 40 mins | 1 | 40
Generator | 3 hours | 30 mins | 1 hour | 10 mins | 5 mins | 4 hours 45 mins | 4 | 45
Energy Cell | 2 hours | 10 mins | 20 mins | 5 mins | 5 mins | 2 hours 40 mins | 2 | 40
Lockers | 1 hour | 10 mins | 5 mins | 5 mins | 5 mins | 1 hour 25 mins | 1 | 25
Large Corridor Window | 10 mins | 10 mins | 10 mins | 5 mins | 5 mins | 40 mins |  | 40
Corridor Doors | 2 hours | 20 mins | 20 mins | 10 mins | 5 mins | 2 hours 55 mins | 2 | 55
Control Center Computers | 4 hours | 1 hour | 30 mins | 10 mins | 5 mins | 5 hours 45 mins | 5 | 45
Control Center Chairs | 1 hour | 10 mins | 10 mins | 5 mins | 2 mins | 1 hour 27 mins | 1 | 27
Control Center Windows | 10 mins | 10 mins | 5 mins | 5 mins | 5 mins | 35 mins |  | 35
Bed | 30 mins | 10 mins | 5 mins | 5 mins | 5 mins | 55 mins |  | 55
Toilet | 30 mins | 5 mins | 5 mins | 2 mins | 3 mins | 45 mins |  | 45
Shower | 30 mins | 5 mins | 5 mins | 2 mins | 2 mins | 44 mins |  | 44
Mechanics Room | 1 hours | 30 mins | 5 mins | 5 mins | 2 mins | 1 hour 42 mins | 1 | 42
[7 empty] | 33 | 12.1333
Total Hours | 45.1333
Script Name | Script Function
Door Manager | This script will control the opening and closing of the corridor doors based on player interaction
Locker Door Manager | This script will control the opening and closing of locker doors based on player interaction
Laser Manager | This script will allow the player to interact with the lasers and shut them off when they have completed certain objectives
Inventory Manager | This will control what objects they have collect and what objects are available to use, such as weapons.
Character Controller | This script will control the walking/ running/ jumping mechanics of the players.
First Person Camera | This script will control the camera movement and placement (may use cinemachine)
Weapon Controller | This will control the players interaction with weapons. Aim, Shoot, Reload, and Swap weapons. (may only allow one weapon)
Animation Integration | This script will manage when animations are triggered.
Model Name | Texture Size | Distance | Maps
Corridor | 2048 Resolution | Very Close | Normal, Height, Metallic, Color, Roughness
Trash Can | 1024 Resolution | Close | Normal, Height, Metallic, Color, Roughness
Bench | 1024 Resolution | Close | Normal, Height, Metallic, Color, Roughness
Generator | 2048 Resolution | Very Close | Normal, Height, Metallic, Color, Roughness
Energy Cell | 1024 Resolution | Very Close | Normal, Height, Metallic, Color, Roughness, Emmission
Lockers | 1024 Resolution | Close | Normal, Height, Metallic, Color, Roughness
Large Corridor Window | 1024 Resolution | Very Close | Normal, Height, Metallic, Color, Roughness, Opacity
Corridor Doors | 2048 Resolution | Very Close | Normal, Height, Metallic, Color, Roughness
Control Center Computers | 2048 Resolution | Very Close | Normal, Height, Metallic, Color, Roughness
Control Center Chairs | 1024 Resolution | Close | Normal, Height, Metallic, Color, Roughness
Control Center Windows | 1024 Resolution | Close | Normal, Height, Metallic, Color, Roughness, Opacity
Bed | 1024 Resolution | Close | Normal, Height, Color,
Toilet | 1024 Resolution | Close | Normal, Height, Color, Metallic, Roughness
Shower | 1024 Resolution | Close | Normal, Height, Color, Metallic, Roughness
Mechanics Room | 2048 Resolution | Close | Normal, Height, Color, Metallic, Roughness
Production Pipeline
DEEP SPACE RESCUE
Deep Space Rescue is a linear survival game that allows players to complete objectives
that will advance their way through the game.
Story:
You are a space rescuer who is tasked with saving space travelers from recent disasters
caused by an unkown space menace, whom you will encounter on one of your rescue missions.
Location | Outer Space
Timeline | Dinstant Future - Year 4027
Game Engine | Made with Unity
Production
1. White boxing will first have to take place to ensure correct placement of the enviormental pieces.
a level map has been created to be a template for this step.
2. Probuilder will be installed in Unity to stream line the whiteboxing
process to make sure the scale is accurate
2a. While white box is set up, the game mechanics can be figured out
2b. Starting with a custom character controller
2c. Camera placement for FPS mechanic
2d.Followed by weapon use
2e. Enemy interaction
2f. Enviormental interaction
3. The modeling will begin in Maya.
4. Each model that will require a 2048 texture map will require a low and a high res model.
5. When the models are completed and UV'd, they will be sent into substance to be textured.
6. As displayed in the Time Budget, each model will have specific maps that will be baked in substance.
7. After models have been textured, they can be imported into
Unity for correct placement and arranging.
8. Animations
8a. Doors opening and closing
8b. Lockers opening and closing
8c. Space rocks floating when looking out windows
8d. Gun recoil
8e. Gun reload
8f. Gun melee